## Project Planner
Timeline of Tasks
[8 empty] | Proposed Duration | [7 empty] | In Progress (Weeks Completed) | [10 empty] | Tasks Completed
S NO | ACTIVITY | PLAN START (WEEK) | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIOD (WEEKS)
[7 empty] | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  |  | APRIL
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
1 | Literature Study on Existing MAVs | 1 | 5 | 1 | 5 | 100%
2 | Study on Birds Exhibiting Mission Characteristics | 3 | 4 | 3 | 4 | 100%
3 | Study on Insects Exhibiting Mission Characteristics | 9 | 3 | 9 | 3 | 100% | bar: OCTOBER 9 to NOVEMBER 11; DECEMBER 14
4 | Sketching | 6 | 6 | 6 | 6 | 100%
5 | Data on Strouhal Number | 9 | 3 | 9 | 3 | 100%
6 | Preliminary Weight Estimation | 10 | 4 | 10 | 4 | 100%
7 | Mathematical Modelling (Model Validation) | 14 | 4 | 14 | 4 | 100%
8 | Configuration Selection | 19 | 13 | 19 | 9 | 0%
9 | Aerodynamic Analysis (Wing, Fuselage) | 22 | 7 | 22 | 6 | 0%
10 | Performance Analysis | 28 | 1
10 | Propulsion System - Survey and Design | 29 | 2
12 | Tail Design and Stability Analysis | 29 | 2
13 | Tradeoff Study | 31 | 1
14 | Sensitivity Analysis | 31 | 1
15 | Feasibility Study (cost, practicality) | 31 | 1
16 | Iterations | 32 | 2